## Seng301-Term Project
WishList.com Task Dependencies |  |  | WishList.com Estimates
|  |  | Task |  | Optimistic (Hour) | Realistic (Hour) | Pessimistic (Hour)
Work Package | Task | Dependency | 1.1. Preliminary Work |  | 56 | 69 | 91
1.1. Preliminary Work | PW1. DB Design |  | PW1. DB Design |  | 5 | 7 | 10
1.1. Preliminary Work | PW2. UI Design | PW1 | PW2. UI Design |  | 17 | 20 | 25
1.1. Preliminary Work | PW3. Achitectural Design | PW2 | PW3. Achitectural Design |  | 21 | 24 | 32
1.1. Preliminary Work | PW4. Technical Documentation | PW3 | PW4. Technical Documentation |  | 5 | 7 | 10
1.1. Preliminary Work | PW5. Determining the Target Audience | PW4 | PW5. Determining the Target Audience |  | 6 | 8 | 10
1.1. Preliminary Work | PW6. Team Indroduction | PW5 | PW6. Team Indroduction |  | 2 | 3 | 4
1.2. Technical Analysis | TA1. Current Computer Hardware Analysis | PW6 | 1.2. Technical Analysis |  | 13 | 18 | 23
1.2. Technical Analysis | TA2. Determining the Necessary Infrastructure Needs | PW6 | TA1. Current Computer Hardware Analysis |  | 3 | 5 | 7
1.2. Technical Analysis | TA3. Adequacy Analysis of Resources | PW6 | TA2. Determining the Necessary Infrastructure Needs |  | 5 | 6 | 7
1.3.1. Authentikation Tasks | AT1.Sign Up | PW6 | TA3. Adequacy Analysis of Resources |  | 5 | 7 | 9
1.3.1. Authentikation Tasks | AT2. Sign In | PW6 | 1.3. Dev |  | 233 | 301 | 387
1.3.1. Authentikation Tasks | AT3. Forget Password | AT2 | AT1.Sign Up |  | 10 | 13 | 17
1.3.2. Back-End | BE1. User-Admin DataBase | PW6 | AT2. Sign In |  | 10 | 11 | 14
1.3.2. Back-End | BE2. Whis List DataBase | PW6 | AT3. Forget Password |  | 10 | 11 | 14
1.3.2. Back-End | BE3. Product DataBase | PW6 | BE1. User-Admin DataBase |  | 13 | 16 | 20
1.3.2. Back-End | BE4. Integration with Amazon Product Search API | PW6 | BE2. Whis List DataBase |  | 13 | 16 | 20
1.3.3. Admin Module | AD1. Manage Permissions | PW6 | BE3. Product DataBase |  | 13 | 16 | 20
1.3.3. Admin Module | AD2. Manage Roles | PW6 | BE4. Integration with Amazon Product Search API |  | 5 | 8 | 12
1.3.3. Admin Module | AD3. Manage Role Permissions | AD1, AD2 | AD1. Manage Permissions |  | 5 | 7 | 11
1.3.3. Admin Module | AD4. Manage Users | PW6 | AD2. Manage Roles |  | 5 | 7 | 11
1.3.3. Admin Module | AD5. Manage User Roles | AD2, AD4 | AD3. Manage Role Permissions |  | 7 | 10 | 13
1.3.3. Admin Module | AD6. Manage Requests | PW6 | AD4. Manage Users |  | 7 | 10 | 13
1.3.3. Admin Module | AD7. Manage Reports | PW6 | AD5. Manage User Roles |  | 7 | 10 | 13
1.3.3. Admin Module | AD8. Block Users | AD5 | AD6. Manage Requests |  | 7 | 10 | 13
1.3.4. Add Wish List Page Module | AWL1. Front-End Developer | BE2, BE3 | AD7. Manage Reports |  | 10 | 14 | 18
1.3.4. Add Wish List Page Module | AWL2. Create URL Page Module | AWL1 | AD8. Block Users |  | 10 | 14 | 18
1.3.5. Other Page Module | OP1. Home Page | PW6 | AWL1. Front-End Developer |  | 24 | 32 | 40
1.3.5. Other Page Module | OP2. Reservation Page | BE4 | AWL2. Create URL Page Module |  | 20 | 24 | 30
1.3.5. Other Page Module | OP3. Settings Page | BE1 | OP1. Home Page |  | 20 | 24 | 30
1.4. DevOps | D1. Server Configuration | PW6 | OP2. Reservation Page |  | 15 | 22 | 28
1.4. DevOps | D2. Staging Deployment | QA2 | OP3. Settings Page |  | 22 | 26 | 32
1.4. DevOps | D3. Prod Deployment | QA3 | 1.4. DevOps |  | 13 | 17 | 22
1.5. QA | QA1. Test Planning | PW6 | D1. Server Configuration |  | 5 | 7 | 10
1.5. QA | QA2. Functional Testing | QA1, AT1 | D2. Staging Deployment |  | 4 | 5 | 6
1.5. QA | QA3. Regression Testing | QA2 | D3. Prod Deployment |  | 4 | 5 | 6
1.5. QA | Q4. Smoke Testing | QA3 | Total Work |  | 315 | 405 | 523
1.6. Other | O1. PM |  | 1.5. QA
1.6. Other | O2. TL |  | QA1. Test Planning | 0.1 | 31.5 | 40.5 | 52.3
1.6. Other | O3. Non Dev | PW6 | QA2. Functional Testing | 0.2 | 63 | 81 | 104.6
1.6. Other | O4. Bug Fix | QA2 | QA3. Regression Testing | 0.2 | 63 | 81 | 104.6
|  |  | Q4. Smoke Testing | 0.01 | 3.15 | 4.05 | 5.23
1.6. Other
|  |  | O1. PM | 0.2 | 63 | 81 | 104.6
|  |  | O2. TL | 0.2 | 63 | 81 | 104.6
|  |  | O3. Non Dev | 0.05 | 15.75 | 20.25 | 26.15
|  |  | O4. Bug Fix | 0.25 | 78.75 | 101.25 | 130.75
|  |  | Grand Total |  | 696.15 | 895.05 | 1155.83